## Sheet1
Date | Tasks/Issues | Veritas Case No. | Remarks
2019-05-16 | Start installation of NBU CloudCatalyst Media server software on hkg3nbupms2.
2019-05-16 | CloudCatalyst Linux Media server installation Error 103 | 190516-000208 | Issue1
2019-05-17 | Find out Veolia installed Linux v8.0 which is not compatible to NBU v8.1.2, after recreate Linux v7.4 server, NBU Media server software can be installed successfully | 190516-000208
2019-05-17 | Configure Cloud Storage Server wizard, the media server name HKG3NBUPMS2 is not shown in the server lists. | 190516-000208 | Issue2
18/5/2019 - 28/5/2019 | Trouble Shooting with Veritas Support Engineers | 190516-000208 | Parag Mahajan, Arjun Kumar Ale
2019-06-04 | Solved by rebooting both NBU Master server & Media server | 190516-000208
2019-06-04 | When run “Cloud Storage Server Configuration Wizard” it prompt “illegal login credential or Certificate” | 190516-000208 | Issue3
2019-06-04 | Passed case to Mr. Kelvin Hai
2019-07-10 | Case#190516-000208 closed
2019-07-15 | Reported Backup error. Solved byTeamviewer remote checking.
2019-07-26 | Reported Duplication jobs failed with status 191 | 190726-000798 | Sachin Chavan
2019-07-30 | Found jobs are failing intermittently due to network connectivity error. | 190726-000798
During troubleshooting we found network bandwidth is not setup for cloud jobs.
In order to avoid load from system we have reduced max i/o streams value from unlimited to 50.
2019-08-16 | Case#190726-000798 closed
2019-08-26 | Reported Since migrated from AWS SG to HK the backup has been failed
2019-08-27 | Replied our findings, but no response from Veolia
2019-11-20 | Requested to trouble shoot "Storage Server down"
2019-11-21 | Open Case " NBU CloudCatalyst Media server -Storage Server is down or unavailable" | 191121-000722
2019-11-25 | Veritas Support Pickup case | 191121-000722 | Harsh Dholepatil
25/11,29/11,2/12, 3/12 | Trouble Shooting with Veritas Support Engineers | 191121-000722
2019-12-03 | Remove all old NBU Configuration of AWS SG CloudStorage on HKG3NBUPMS2 from the NBU Master server. | 191121-000722
New create Cloud Storage Server of AWS HK CloudStorage on HKG3NBUPMS2
Tested Backup OK
2019-12-04 | Case#191121-000722 closed
2020-01-20 | Open Veritas case | 200120-000136
2020-01-21 | Remote support perform cache backup
2020-01-22 | EEB install
2020-01-23 | Remote troubleshoot Customer to be back on 3rd Feb
2020-02-03 | Support shift is changed Case redispatched
2020-02-04 | Case was redispatched and escalated
2020-02-05 | Remote Support collect log
2020-02-06 | Remote Support collect log
2020-02-07 | Remote Support collect log
2020-02-10 | Remote Support collect log
2020-02-11 | Case escalated